## Slide 1
OLMS
GROUP 1 / MEMBERS 1–6
Release One
Review & leadership transition
Muhammad Huzaifa Asif
Nazir Imran
Outgoing project manager
Incoming project manager
Notes: Presenter: Member 1. Introduce Group 1, Release 1 review, and the planned transfer of project management to Member 2.

## Slide 2
Project charter
02
MEMBER 1
Area | Agreement
Purpose | Replace paper records with a simple library web application.
Users | Librarian, library administrator, members and college management.
Duration and team | Eight project weeks, four releases, six members.
Core scope | Catalogue, copies, members, borrowing, returns and overdue listing.
Technology | Python, Flask, SQLite, HTML and CSS.
Boundaries | No payments, barcode hardware or institutional integration.
Success | Accurate records, usable borrowing workflow and passed acceptance checks.
Notes: One-page charter. The eight-week duration and four releases are project planning assumptions established in the discussion. No budget or formal acceptance is claimed.

## Slide 3
Product goal and release roadmap
03
MEMBER 1
A reliable small-library system that helps staff find books and manage loans.
Release | Focus | Expected result
R1 • Weeks 1–2 | Catalogue and members | Staff can maintain books, copies and member status.
R2 • Weeks 3–4 | Borrowing and returns | Staff can issue and return copies. MVP target.
R3 • Weeks 5–6 | Overdue loans | Staff can identify overdue loans. History if time permits.
R4 • Weeks 7–8 | Quality and reporting | Regression checks and documentation. Optional CSV/filtering.
Notes: Release 1 and borrowing/returns in Release 2 follow the current plan. Release 3 and Release 4 allocation is proposed for agreement.

## Slide 4
Member work fields
04
MEMBER 1
Member | Release 1 work field | Release 2 responsibility
Member 1 | Project management / Scrum | Handover support and requirements review
Member 2 | Requirements and product backlog | Project manager / Scrum
Member 3 | Backend development and authentication | Borrowing and return logic
Member 4 | Database and record management | Loan records and data integrity
Member 5 | Frontend development | Borrowing and return pages
Member 6 | Testing and documentation | Acceptance checks and release evidence
Responsibility allocation for team confirmation.
Notes: This is the proposed responsibility allocation for this deck. Confirm it against actual contributions. Do not claim that a member completed work solely because it appears in this allocation.

## Slide 5
Release 1 sprint goal and scope
05
MEMBER 2
Staff can maintain a searchable catalogue and register members with eligibility status.
Catalogue
Register and edit books. Search by title or author.
Physical copies
Assign unique copy IDs and show available / total counts.
Access and membership
Staff login/logout. Register members and change active status.
Record preservation
Deactivate and reactivate books without deleting their records.
Notes: The current code implements all seven areas. Borrowing, returning and overdue tracking are outside Release 1.

## Slide 6
Prioritised product backlog
06
MEMBER 2
IDs | Backlog items | Priority | Release
PB-01–03 | Staff login, book registration, physical copies | Must | R1
PB-04–05 | Title/author search, edit and deactivate books | Must | R1
PB-06–07 | Member registration and eligibility | Must | R1
PB-08–09 | Borrowing with due dates, returns | Must | R2
PB-10 | Overdue loan listing | Must | R3
PB-11 | Borrowing history | Should | R3
PB-12–13 | Category filtering and CSV exports | Could | R4
Notes: PB-01 to PB-07 are implemented in the supplied Release 1 package. Remaining work is planned. R3/R4 allocation is proposed. Optional items can move if core work needs more time.

## Slide 7
Release 1 acceptance criteria
07
MEMBERS 3–6
Feature | Acceptance check | Lead
Staff access | Correct login succeeds. Wrong password fails. Logout protects pages. | M3
Books and copies | Book gets a unique ID. Three copies get three distinct IDs. | M4
Search | Partial English title/author search works regardless of letter case. | M3 / M5
Book maintenance | Edits preserve IDs. Deactivation hides book from default catalogue. | M3 / M4
Members | Valid name creates a unique member ID. Blank name is rejected. | M4 / M5
Eligibility | Active displays ELIGIBLE. Inactive displays NOT ELIGIBLE. | M3 / M6
Persistence | Records remain after stopping and restarting the application. | M6
Notes: Owners are working assignments. Each item requires actual team test evidence before the team marks it Done.

## Slide 8
Release 1 progress and evidence
08
MEMBER 6
Evidence level | Current position
Demonstrated locally | Application runs locally and staff login succeeds.
Demonstrated catalogue record | B-1: HSK 1 Standard Course. Active. Three available / three total.
Implemented and automatically checked | All seven Release 1 areas in the supplied code package.
Team verification still needed | Search, editing, separate copy IDs, member status and restart evidence.
Acceptance status | Team review and acceptance record remain pending.
The edition field currently contains a publisher name. Correct it before the demo.
Notes: Source: user screenshots dated 24 October 2026, including Weixin Image_20261024140832_1213_92.png. Automated Flask test-client checks passed during preparation of the source package. Team manual acceptance and shared repository evidence have not been supplied.

## Slide 9
Definition of Done and release evidence
09
MEMBER 6
Feature complete
Acceptance criteria pass and another member reviews the code.
Quality checked
Normal and invalid inputs pass. No blocking defect remains.
Records protected
Changes save correctly and existing data survives restart.
Evidence recorded
Shared repository, test results and setup guide support the demo.
Notes: Explain that passing automatic checks does not establish team acceptance. Repository link is pending and must be inserted by the group before submission.

## Slide 10
Release 1 review and demonstration
10
MEMBER 1 WITH MEMBER 6
Order | Demonstration | Expected result
1 | Log in and open the catalogue | Authorised staff access
2 | Open B-1 and add two physical copies | Five total copies with distinct IDs
3 | Search, edit, deactivate and reactivate | Correct result and preserved IDs
4 | Register a member and toggle status | Eligibility changes with status
5 | Restart, log in and check records | Saved records remain
Review record: date, tester, expected result, actual result, pass/fail and open issues.
Notes: Run these steps live. Present only results actually observed. The shared repository URL and review record are still pending.

## Slide 11
Project manager handover
11
MEMBER 1, THEN MEMBER 2
Member 1 • Outgoing manager | Member 2 • Incoming manager
Summarise Release 1 scope and demonstrated progress. | Confirm the current baseline and outstanding checks.
Transfer source files, backlog and setup instructions. | Lead Release 2 planning and daily coordination.
Explain defects, risks and acceptance gaps. | Assign owners and monitor progress against the sprint goal.
Support questions during the transition. | Lead the sprint review and record release decisions.
Handover record: repository access, runnable version, backlog, test log and open issues.
Notes: Member 1: I am handing over the current scope, working source, test status and open issues. Member 2: I will lead the next sprint, confirm priorities, assign daily work and track blockers. This slide presents the planned handover, not a claim that sign-off has already happened.

## Slide 12
Release 2 sprint goal
12
MEMBER 2
Staff can issue an available copy to an active member and record its return.
Borrowing
Validate the member and copy. Save the loan and due date.
Availability
Issuing a copy reduces availability. Returning restores it.
Integrity
Reject inactive members, unavailable copies and repeat returns.
MVP target
Catalogue, authentication, members, borrowing and returns work together.
Notes: This is the incoming manager’s proposed plan. The team must agree the loan period and due-date policy on Day 1. No loan duration is assumed here.

## Slide 13
Release 2 plan: first five working days
13
MEMBER 2
Day | Work | Lead members | Daily result
1 | Confirm loan rules, acceptance checks and open R1 issues. | M2, M1, M6 | Agreed sprint backlog
2 | Design loan table and member/copy relationships. | M4, M3 | Reviewed data design
3 | Build borrowing logic and eligibility checks. | M3, M4 | Loan saves with valid data
4 | Build issue form and clear validation messages. | M5, M3 | Usable borrowing page
5 | Integrate borrowing and test invalid cases. | M6, M3–5 | Borrowing demo and defect log
Daily coordination: completed work, next task, blocker and responsible member.
Notes: This is a proposed ten-working-day plan. Member 2 leads the daily check-in. Member 1 supports requirements review after the handover.

## Slide 14
Release 2 plan: next five working days
14
MEMBER 2
Day | Work | Lead members | Daily result
6 | Build return logic and restore copy availability. | M3, M4 | Correct return transaction
7 | Build loan lookup and return page. | M5, M3 | Usable return workflow
8 | Test full issue/return flow and R1 regression. | M6, M3–5 | Recorded test results
9 | Fix defects, check restart and update user guide. | M3–6 | Release candidate
10 | Demonstrate, review criteria and record decision. | M2, all members | Review and next backlog
Member 2 tracks progress and escalates blockers throughout both weeks.
Notes: The second week completes returns and checks the integrated MVP. Release acceptance depends on the recorded review.

## Slide 15
Release 2 acceptance and risks
15
MEMBER 2 WITH MEMBER 6
Check or risk | Expected behaviour / response
Valid borrowing | One available copy links to one active member with a due date.
Unavailable copy or inactive member | Borrowing fails without creating a loan.
Repeated borrowing or return | No duplicate active loan and no double increase in availability.
Return and persistence | Loan closes, copy becomes available and restart retains records.
Database changes | Back up current data and test changes on a separate copy.
Time or integration problems | Prioritise borrowing/returns and defer optional features.
Notes: Proposed acceptance checks. Due-date rules need agreement on Day 1. Preserve the current database and back it up before schema changes.

## Slide 16
Review decisions and next actions
16
MEMBER 1 AND MEMBER 2
Release 1
Record remaining manual checks and the review decision.
Manager transition
Confirm Member 2’s coordination role and access to project materials.
Release 2
Agree the proposed sprint backlog and ten-day work plan.
Submission pack
Attach the shared repository link, setup evidence and test log.
Notes: Close with the actual decisions recorded at the meeting. Do not describe pending acceptance or repository access as complete. The teacher’s Week 5 checklist requires charter, goal/backlogs, criteria, Definition of Done, shared repository and setup evidence.

## Slide 17
GitHub Repository Link
17
 | https://github.com/021Engr-imran/OLMS
Notes: Close with the actual decisions recorded at the meeting. Do not describe pending acceptance or repository access as complete. The teacher’s Week 5 checklist requires charter, goal/backlogs, criteria, Definition of Done, shared repository and setup evidence.